## Sheet1
Date | Project | Content | Status | Difficulty | Owner | Comment
2017-07-03 | 周目标对齐 | LBA test_list finished |  | 1 | zhilong/weifeng
|  | GRB test |  | 1 | hongyi/weili
|  | NVC test cases review and test | done this week | 2 | zhilong/weifeng
|  | venus LBA test cases develop | finished at 8.3
|  | 1) write/read/testtool |  | 2 | yingjun
|  | 2) error handle | done this week | 2 | shaobin
|  | 2) atomic/multNS/MDTS/SGL/PRP |  | 2 | liangmin/chenchen | atomic finisehd/ multNS doing
|  | 3) interface/PI/LBA invalid/AES/scramble | start next week | 2 | zhilong/weifeng
|  | 4) powercycle/format/dataset/GC | GC doing, done in two weeks | 2 | hongyi/weili
|  | SDK1.1 test/release |  |  | fangwu/shaobin/chenchen/zhilong
|  | 1) regression script improve |  | 1 | liangmin | reg_all_v2.py
|  | HostFTL |  |  | yingjun
|  | 1) WLP QLC |  | 1 | yingjun
|  | 2) WL new version | done this week | 1 | yingjun
|  | 3) test cases | Done at the end of July | 2 | yingjun
|  | LightNVM test cases | done this week |  | beishi
|  | 1) Rocksdb new tc |  | 2 | beishi
|  | 2) merge old test cases |  | 1 | beishi
|  | testrail demo | done this week | 2 | shaobin
venus PPA test cases develop
|  | 1) LPA | Done at the end of July | 2 | Beishi Chen
|  | 2) Dual/quart plane | done this week | 1 | fangwu
|  | 3) AES | done this week | 1 | fangwu
|  | SQL test (LightNVM) |  | 2 | chenchen
|  | netboot | done this week | 1 | yingjun/chenchen